## Slide 1: Estimation
The process of predicting the most realistic amount of effort
expressed in terms of person-hours or money
required to develop or maintain software based on incomplete, uncertain and noisy input.
Effort estimates may be used as input to project plans, iteration plans, budgets, investment analyses, pricing processes and bidding rounds.

## Slide 2: How to Estimate Cost and Effort
1. Map Your Software Development Life Cycle
2. Check Your Project Requirements
3. Make a Work Breakdown Structure
4. Use a Software Estimation Technique

## Slide 3: Role in communication
Resource Allocation
Improving Team Morale
Managing Stakeholder Expectations
Product Quality and Technical Debt

## Slide 4: Estimation techniques

## Slide 5: Estimation techniques
Organizations need to make software effort and cost estimates.
  Experience-based techniques The estimate of future effort requirements is based on the manager’s experience of past projects and the application domain. Essentially, the manager makes an informed judgment of what the effort requirements are likely to be.
  Algorithmic cost modeling In this approach, a formulaic approach is used to compute the project effort based on estimates of product attributes, such as size, and process characteristics, such as experience of staff involved.

## Slide 6: Estimate uncertainty

## Slide 7: Experience-based approaches
Experience-based techniques rely on judgments based on experience of past projects and the effort expended in these projects on software development activities.
Typically, you identify the deliverables to be produced in a project and the different software components or systems that are to be developed.
You document these in a spreadsheet, estimate them individually and compute the total effort required.
It usually helps to get a group of people involved in the effort estimation and to ask each member of the group to explain their estimate.

## Slide 8: Problem with experience-based approaches
The difficulty with experience-based techniques is that a new software project may not have much in common with previous projects.
Software development changes very quickly and a project will often use unfamiliar techniques such as web services, application system configuration or HTML5.
If you have not worked with these techniques, your previous experience may not help you to estimate the effort required, making it more difficult to produce accurate costs and schedule estimates.

## Slide 9: Algorithmic cost modelling
Cost is estimated as a mathematical function of product, project and process attributes whose values are estimated by project managers:
  Effort = A ´ SizeB ´ M
  A is an organisation-dependent constant, B reflects the disproportionate effort for large projects and M is a multiplier reflecting product, process and people attributes.
The most commonly used product attribute for cost estimation is code size.
Most models are similar but they use different values for A, B and M.

## Slide 10: Estimation accuracy
The size of a software system can only be known accurately when it is finished.
Several factors influence the final size
  Use of reused systems and components;
  Programming language;
  Distribution of system.
As the development process progresses then the size estimate becomes more accurate.
The estimates of the factors contributing to B and M are subjective and vary according to the judgment of the estimator.

## Slide 11: Effectiveness of algorithmic models
Algorithmic cost models are a systematic way to estimate the effort required to develop a system. However, these models are complex and difficult to use.
There are many attributes and considerable scope for uncertainty in estimating their values.
This complexity means that the practical application of algorithmic cost modeling has been limited to a relatively small number of large companies, mostly working in defense and aerospace systems engineering.

## Slide 12: Popular techniques

## Slide 13: PERT Estimation
The Program Evaluation and Review Technique (PERT) is a statistical estimation technique used to estimate the time required to complete a project by considering the expected duration of each task and the dependencies between them.
PERT estimation is particularly useful for large and complex projects.
It helps teams to account for the dependencies and has the potential to provide a more accurate estimation of the overall project duration.
But it can be time-consuming and requires a lot of information about the project.
Good for: Large teams (though works at any size), complex and uncertain projects, and projects requiring risk management.
PERT Estimate = (O + 4 x M) + P) / 6. (M)ost likely (O)ptimistic (P)essimistic

## Slide 14: Analogous Estimation
This method estimates the effort required to complete a project by comparing it to similar past projects.
Start by identifying similar past projects and estimate the effort required to complete the current project based on the effort required for the past projects. This process is particularly useful when dealing with similar projects or tasks.
You need to watch out for false positives – some similar-looking tickets may not be so simple under the hood. Diving deeper into requirements can help.
Good for: Any situation where historical data is available and easy to access and analyse, unless you have AI help. You'll need strong codebase knowledge (or AI) in your team to capitalize on this method.

## Slide 15: Agile estimation
Collaborative: Involving everyone on the Agile development team because collaborative efforts lead to better estimates.
Faster than any traditional techniques. It recognizes that estimations are a non-value-added activity and tries to minimize them.
Estimation is not in terms of dollars or days; instead, “points” or qualitative labels are employed for estimating or comparing tasks.
Top down
Retrospectives help refine the estimates for future

## Slide 16: Story points
Unit of measure to define effort
Consider:
1. Complexity
2. Risk – random changes, unclear requirements, dependencies
3. Familiarity with the area
4. Estimation matrix (e.g., Fibbonnacci)

## Slide 17: Process flow
Identify user stories.
Discuss the user story requirements.
Formulate an estimation matrix: Numeric scale that helps evaluate the selected task. E.g., Fibonacci sequence (…5, 8, 13…) or the linear scale (… 3, 4, 5…).
Select a suitable Agile estimation technique
Carry out sprint planning
Ensure that the estimate consistency

## Slide 18: Sprint velocity
The number of story points that a specific team can complete in a sprint.
Calculated using historical data.

## Slide 19: Three-Point Method
The Three-Point Method is used to estimate the time required to complete a project by considering the best-case, worst-case, and most-likely scenarios.
Using three values: optimistic, pessimistic, and realistic. The average of the three values is then used to calculate the overall estimation.
Useful when dealing with uncertain tasks or projects.
One problem with the Three-Point Method is that it sometimes doesn't yield accurate estimates for uncertain tasks or projects.
Good for: Large teams (though works at any size), complex and uncertain projects.

## Slide 20: Planning Poker
Consensus-based estimation technique.
Team members estimate the effort required for each task using a deck of cards with numerical values. The team then discusses their estimates and tries to come to a consensus for a story point estimate.
Could be time consuming
Good for: small to medium-sized teams, small- to medium-sized projects, and projects with uncertainty about scope or complexity.

## Slide 21: T-shirt sizing
T-Shirt Sizing is an estimation technique used to estimate the effort required to complete a project by assigning t-shirt sizes (e.g., small, medium, large, extra-large) to tasks.
Its simplicity attracts many agile teams as a method to assign story points, but it's a magnet for inaccurate estimations. It's just too reliant on subjective opinions rather than objective data, and too reliant on a system that is open to interpretation – in my experience projects driven by T-shirt sizing often go sideways unexpectedly.

## Slide 22: Bucket system
This one's really similar to our T-shirts. It works by dividing the project into buckets or categories based on the level of effort required. Too much lack of clarity, too much opinion.

## Slide 23: Large Small Uncertain (LSU)
LSU categorises tasks based on their size and uncertainty. Identify the tasks required to complete the project and categorize them as large, small, or uncertain.
The effort required for each category is then estimated, and the total effort for the project is calculated.
It may be difficult to categorize tasks accurately, especially if the team members have difference of opinion. It's important to ensure that the team has a shared understanding of the task categorization before starting the estimation process.
Good for: Teams with strong codebase knowledge. Projects with uncertainty and risk.

## Slide 24: Cost
Total points for backlog = 1000
Velocity after 2 sprints = 100
Total no of sprints needed = 1000/100 = 10
Resource cost per sprint = $900
Resource cost for whole project = $900 x 10 = $9,000

## Slide 25: The future of estimation
Human estimation is flawed. Our experiences and cognitive limitations bias us.
AI based methods can leverage vast amounts of data and sophisticated algorithms to generate highly accurate predictions that are free from human bias.
As AI-powered prediction models continue to evolve and improve, they will become an essential project planning tool for any organization that wants to stay ahead of the competition.

## Slide 26: References
https://www.projectmanager.com/blog/software-development-estimation
https://softwaredominos.com/home/software-design-development-articles/software-effort-estimation-how-to-get-it-right-the-first-time/
https://www.netsolutions.com/insights/how-to-estimate-projects-in-agile/
https://www.stepsize.com/blog/the-best-software-estimation-techniques